## Sheet1
Description of Known Issue | Location | Date Identified | Current Status (Open, Closed, In Progress) | Disposition (Planned, Deferred, In Progress) | Remediation Timeline | Available Workarounds | Additional Comments
Criterion 2.4.7 (WCAG 2.1) Focus Visible: Any keyboard operable user interface has a mode of operation where the keyboard focus indicator is visible. (Level AA) When navigating the site using the keyboard there is no visual indicator to show the user which anchor or link is currently selected. | Sitewide | 2019-10-01 | Closed | Complete | Completed October 2020 | N/A
Criterion 1.4.3 (WCAG 2.1) Contrast (minimum) The visual presentation of text and images of text has a contrast ratio of at least 4.5:1 (Level AA) There is low contrast text throughout the site. | Sitewide | 2019-10-01 | Closed | Complete | Completed October 2020 | N/A
Criterion 1.4.3 (WCAG 2.1) Contrast (minimum) The visual presentation of text and images of text has a contrast ratio of at least 4.5:1 (Level AA) There is low contrast text throughout the site. | Sitewide | 2019-10-01 | Closed | Complete | Completed October 2020 | N/A
Criterion 1.4.3 (WCAG 2.1) Contrast (minimum) The visual presentation of text and images of text has a contrast ratio of at least 4.5:1 (Level AA) There is low contrast text throughout the site. | Sitewide | 2019-10-01 | Closed | Complete | Completed October 2020 | N/A
Criterion 1.1.1 (WCAG 2.1) 1.1.1 Non-text Content: All non-text content that is presented to the user has a text alternative that serves the equivalent purpose, except for the situations listed below. (Level A) Some images do not have a text alternative, so people using a screen reader cannot access the information. | Microsites/subdomains www.eqhria.scottishhumanrights.com & www.careaboutrights.scottishhumanrights.com | 2019-10-01 | Open | In progress | Due for completion October 2022 | These sites are archives, we are working on migrating the information contained on these sites over to the main website platform. | Migration to an accessible platform underway in March 2022
Criterion 2.4.7 (WCAG 2.1) Focus Visible: Any keyboard operable user interface has a mode of operation where the keyboard focus indicator is visible. (Level AA) When navigating the site using the keyboard there is no visual indicator to show the user which anchor or link is currently selected. | Microsites/subdomains www.eqhria.scottishhumanrights.com & www.careaboutrights.scottishhumanrights.com | 2019-10-01 | Open | In progress | Due for completion October 2022 | These sites are archives, we are working on migrating the information contained on these sites over to the main website platform. | Migration to an accessible platform underway in March 2022
Criterion 2.4.1 (WCAG 2.1) 2.4.1 Bypass Blocks: A mechanism is available to bypass blocks of content that are repeated on multiple Web pages. (Level A) There is no option to skip navigation or skip repeated content. | Microsites/subdomains www.eqhria.scottishhumanrights.com & www.careaboutrights.scottishhumanrights.com | 2019-10-01 | Open | In progress | Due for completion October 2022 | These sites are archives, we are working on migrating the information contained on these sites over to the main website platform. | Migration to an accessible platform underway in March 2022